## Bug_Report
Bug ID | Module | Test Case ID | Bug Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status
BUG_LIB_01 | Library | TC_LIB_03 | Actions column becomes hidden after clicking hamburger menu, causing user confusion | 1. Login to application 2. Navigate to Library page 3. Verify Actions column is visible 4. Click hamburger (☰) menu 5. Observe table layout | Actions column should remain visible or table should auto-adjust when hamburger menu is clicked | Actions column moves out of visible screen and appears only after horizontal scrolling | Medium | Medium | Open
BUG_CODE_02 | Coding Questions | TC_CODE_04 | Incorrect sample input handling causes valid code to fail with InputMismatchException | 1. Login to application 2. Create multiple Java coding questions with sample input 3. Start sample test 4. Write correct Java code using Scanner 5. Click Run Code 6. Observe InputMismatchException 7. Remove sample input and run again | Each coding question should use its own correct sample input and valid code should execute successfully | Same sample input is reused/incorrectly injected, causing InputMismatchException; code works only after removing sample input | Critical | High | Open
BUG_TMP_03 | Template Management | TC_TMP_07 | Programming duration field allows unlimited values when editing template | 1. Login to application 2. Navigate to Templates page 3. Select an existing template 4. Click Edit Template 5. Enter 120000 minutes in Programming Duration 6. Save template | Programming duration should be restricted to a maximum allowed limit (e.g., 300 minutes) | System accepts extremely high values (e.g., 120000 minutes) without validation | High | High | Open

## Test_Scenarios
Scenario ID | Module | Scenario Description
TS_01 | Login | Verify login with valid credentials
TS_02 | Login | Verify error message with invalid credentials
TS_03 | Library | Verify Actions column visibility on Library page
TS_04 | Question Creation | Verify question creation with valid inputs
TS_05 | Test Scheduling | Verify scheduling test with past date

## Test_Cases
Test Case ID | Module | Description | Precondition | Steps | Expected Result | Status
TC_L_01 | Login | Verify login with valid credentials | User is on login page | 1. Enter valid email 2. Enter valid password 3. Click Login | User should be logged in successfully | Pass
TC_L_02 | Login | Verify login with invalid password | User is on login page | 1. Enter valid email 2. Enter invalid password 3. Click Login | Error message should be displayed | Pass
TC_LIB_03 | Library | Verify Actions column visibility after clicking hamburger menu | User logged in and on Library page | 1. Verify Actions column visible 2. Click hamburger menu | Actions column should remain visible | Fail

## RTM
Requirement ID | Requirement Description | Test Case ID | Status
RQ_01 | User Login | TC_L_01, TC_L_02 | Pass
RQ_02 | Library Actions Column Visibility | TC_LIB_03 | Fail
RQ_03 | Question Creation | TC_Q_01 | Not Tested